## Slide 1: Project Management II
Program Evaluation and Review Technique - PERT
Ing. Radomír Perzina, Ph.D.
Operational Analysis for Economists
INMBAOAE

## Slide 2
Outline of the lecture
History
Probability distribution
Expected time
Mean value of a project length
Example

## Slide 3
PERT
The Program (or Project) Evaluation and Review Technique, commonly abbreviated PERT, is a statistical tool, used in project management
Designed to analyze and represent the tasks involved in completing a given project.
First developed by the US Navy in the 1950s.

## Slide 4
PERT
Project analysis – stochastic approach
The time of each activity is a random variable with β-distribution of probability on <a,b>.
Let be a mean of such an activity, while m be a mode (most probable value)

## Slide 5
PERT History
PERT was developed primarily to simplify the planning and scheduling of large and complex projects.
It was developed for the U.S. Navy Special Projects Office in 1957 to support the U.S. Navy's Polaris nuclear submarine project.
It found applications all over industry. An early example was it was used for the 1968 Winter Olympics in Grenoble which applied PERT from 1965 until the opening of the 1968 Games.
This project model was the first of its kind, a revival for scientific management, founded by Frederick Taylor (Taylorism) and later refined by Henry Ford (Fordism). DuPont's critical path method was invented at roughly the same time as PERT.

## Slide 6
PERT History
Initially PERT stood for Program Evaluation Research Task, but by 1959 was already renamed. It had been made public in 1958 in two publications of the U.S. Department of the Navy, entitled Program Evaluation Research Task, Summary Report, Phase 1. and Phase 2. In a 1959 article in The American Statistician the main Willard Fazar, Head of the Program Evaluation Branch, Special Projects Office, U.S. Navy, gave a detailed description of the main concepts of the PERT.
Ten years after the introduction of PERT in 1958 the American librarian Maribeth Brennan published a selected bibliography with about 150 publications on PERT and CPM, which had been published between 1958 and 1968.

## Slide 7
β-distribution

## Slide 8
PERT
optimistic time (a): the minimum possible time required to accomplish a task, assuming everything proceeds better than is normally expected
pessimistic time (m): the maximum possible time required to accomplish a task, assuming everything goes wrong (but excluding major catastrophes).
most likely time (b): the best estimate of the time required to accomplish a task, assuming everything proceeds as normal.

## Slide 9
PERT
Expected time (TE): the best estimate of the time required to accomplish a task, accounting for the fact that things don't always proceed as normal (the implication being that the expected time is the average time the task would require if the task were repeated on a number of occasions over an extended period of time).
Standard deviation:
Calculations: use of expected time for CPM calculations

## Slide 10
PERT
Result of calculation – critical path. In the case of PERT, this value is just a mean value of a project length, with respective standard deviation of a project length.
Mean value of a project length
Standard deviation of the project length

## Slide 11
PERT
Therefore, the main task in this type of project is a calculation of the probability that the project will be finished in time Tp
A length of a project T can be approximated by a normal distribution with a mean , and the standard deviation s(T).
Calculation of probability:
where F is a distribution function of N(0,1)

## Slide 12
PERT – Critical Path
The critical path is determined by adding the times for the activities in each sequence.
Determining the longest path in the project.
The critical path determines the total calendar time required for the project.
If activities outside the critical path speed up or slow down (within limits), the total project time does not change.
The amount of time that a non – critical path activity can be delayed without the project is referred to as a slack time.

## Slide 13
PERT – Critical Path
Critical Path is helpful to determine
  ES – Earliest Start time
  EF - Earliest Finish time
  LS – Latest Start time
  LF - Latest Finish time
The variance in the project completion time can be calculated by summing the variances in the completion times of the activities in the critical path.
The project can be accelerated by adding the resources required to decrease the time for the activities in the critical path.
Shortening of the project sometimes is referred to as Project Crashing.

## Slide 14
PERT - Example
For the project set in a graph and in table, find
Critical path
Calculate the project length mean
Calculate the standard deviation of the project length mean
Calculate the probability that the project will be finished in 42 days
Calculate the probability that the project will be finished in 35 days

## Slide 15
PERT - Example
B
A
D
E
C
G
F
I
H
K
L
1
2
3
4
5
6
7
J

## Slide 16
PERT - Example
5
6
10
0
6
2
5
8
7
9
7
12
16/36
64/36
64/36
0
4/36
4/36
64/36
16/36
4/36
64/36
4/36
4/36

## Slide 17
PERT - Example

## Slide 18
PERT - Example
Critical path (1,4), (4,5), (5,6), (6,7)
Mean value of the project length:
Variance of the project length:
Standard deviation of the project length:

## Slide 19
PERT - Example
Calculate the probability that the project will be finished in 42 days
Calculate the probability that the project will be finished in 35 days

## Slide 20
PERT - Example
Statistical tables – values of N(0,1)
  F(1.48) = 0.43056
  F(1.97) = 0.47558.
Probabilities:

## Slide 21
Advantages
PERT chart explicitly defines and makes visible dependencies (precedence relationships) between the work breakdown structure (commonly WBS) elements.
PERT facilitates identification of the critical path and makes this visible.
PERT facilitates identification of early start, late start, and slack for each activity.
PERT provides for potentially reduced project duration due to better understanding of dependencies leading to improved overlapping of activities and tasks where feasible.
The large amount of project data can be organized and presented in diagram for use in decision making.
PERT can provide a probability of completing before a given time.

## Slide 22
Disadvantages
There can be potentially hundreds or thousands of activities and individual dependency relationships.
PERT is not easily scalable for smaller projects.
The network charts tend to be large and unwieldy, requiring several pages to print and requiring specially-sized paper.
The lack of a timeframe on most PERT/CPM charts makes it harder to show status, although colours can help, e.g., specific colour for completed nodes.

## Slide 23
Uncertainty in project scheduling
During project execution, however, a real-life project will never execute exactly as it was planned due to uncertainty.
This can be due to ambiguity resulting from subjective estimates that are prone to human errors or can be the result of variability arising from unexpected events or risks.
The main reason that PERT may provide inaccurate information about the project completion time is due to this schedule uncertainty.
This inaccuracy may be large enough to render such estimates as not helpful.

## Slide 24
Points to remember
Probability distribution
Optimistic time
Pessimistic time
Most likely time
Expected time
Standard deviation
Mean value
Critical path

## Slide 25
Thank you for your attention