## Slide 1: WBS, task, durations
How to create WBS of your project
Taks, durations and linkages between tasks
Time estimations for project activities
Project Management

## Slide 2
How the lecture will be conducted?
The lecture is divided into three blocks, where each block introduces an issue (1. Project planning, 2. MS Project WBS, 3. MS Project tasks and durations)
After each block there is a quiz for feedback on whether you have understood everything.
We use MS Teams, a shared whiteboard for your engagement and reactions. Also we are working with MS Project.
The class is supplemented with quizzes in vevox, the link is always in the presentation.

## Slide 3
Contents
PART (40 min.)
Project planning, theoretical overview.
2. PART (20 min.)
MS Project WBS, introducing the WBS in MS Project.
3. PART (30 min.)
MS Project tasks and durations, demonstration of how to create tasks, define the duration of each task.

## Slide 4
Learning objectives
After studying this topic, you should be able to:
Divide the project into subparts.
Using the Work Breakdown Structure.
Learn how to use WBS in MS Project.
Create tasks and define their times in MS Project, working with Gantt chart.

## Slide 5
Key readings
You can find support in the following sources:
Book – Chatfield and Johnson (2016). MS Project 2016 Step by Step (Part 3 Start a new plan, Part 4 Build a task list)
Book – Heldman, K. PMP Project Management Profesional Exam – Study Guide (2013). Chapter 3 (Creating the WBS, Plan Scope Management)
MS Project Tutorials – basic setup, tasks:
https://www.youtube.com/watch?v=sYy-iFzz1Eo
https://www.youtube.com/watch?v=tuCrTKMPu_Y

## Slide 6
PART 1
Project planning
Typical problems with developing objectives include:
Project objectives/goals are not agreeable to all parties.
Project objectives are too rigid to accommodate changing priorities.
Insufficient time exists to define objectives well.
Objectives are not adequately quantified.
Objectives are not documented well enough.
Efforts of client and project personnel are not coordinated.
Personnel turnover is high.

## Slide 7
Project Planning
These information requirements are:
The statement of work (SOW)
The project specifications
The milestone schedule
The work breakdown structure (WBS)
The statement of work (SOW) is a narrative description of the work to be accomplished. It includes the objectives of the project, a brief description of the work, the funding constraint if one exists, and the specifications and schedule.

## Slide 8
Project Planning
The successful accomplishment of both contract and corporate objectives requires a plan that defines all effort to be expended, assigns responsibility to a specially identified
Organizational element, and establishes schedules and budgets for the accomplishment of the work.
Development of the work breakdown structure (WBS). A WBS is a product-oriented family tree subdivision of the hardware, services, and data required to produce the end product.

## Slide 9
Project Planning
Preparation of the WBS also considers other areas that require structured data, such as scheduling, configuration management, contract funding, and technical performance parameters.

## Slide 10
Project Planning
Although a variety of work breakdown structures exist, the most common is the six-level indented structure.
The work breakdown structure can be used to provide the basis for:
  The responsibility matrix
  Network scheduling
  Costing
  Risk analysis
  Organizational structure
  Coordination of objectives
  Control (including contract administration

## Slide 11
Project Planning
Work breakdown structure for objective control and evaluation
The WBS must be accompanied by a description of the scope of effort required, or else only those individuals who issue the WBS will have a complete understanding of what work has to be accomplished.
Source: Kerzner, H. 2017. Project Management

## Slide 12
Project Planning
In setting up the work breakdown structure, tasks should:
Have clearly defined start and end dates
Be usable as a communications tool in which results can be compared with expectations
Be estimated on a “total” time duration, not when the task must start or end
Be structured so that a minimum of project office control and documentation (i.e., forms) is necessary
For large projects, planning will be time phased at the work package level of the WBS.
The work package has the following characteristics:
Represents units of work at the level where the work is performed
Clearly distinguishes one work package from all others assigned to a single Functional group
Contains clearly defined start and end dates that are representative of physical accomplishment
Specifies a budget in terms of dollars, man-hours, or other measurable units

## Slide 13
Project planning
On simple projects, the WBS can be constructed as a “tree diagram” or according to the logic flow.
The second method is to create a logic flow and cluster certain elements to represent tasks and projects.
In the tree method, lower-level functional units may be assigned to one, and only one, work element, whereas in the logic flow method the lower level functional units may serve several WBS elements.
Source: Kerzner, H. 2017. Project Management

## Slide 14
Vevox questions
https://silesianuniversity.vevox.com/#/meeting/449222/polls

## Slide 15
PART 2
MS Project WBS
Introducing the WBS in MS Project
For orientation between tasks, it is advisable to structure the project into several phases, i.e. to create a hierarchical structure of activities - WBS (Work Breakdown Structure).
For easier orientation it is recommended to insert a new column (right mouse button in column header → insert new column "WBS code", this will create a sequential outline and de-composition of the individual tasks.

## Slide 16
MS Project WBS
When entering tasks sequentially, it is necessary to create a "task indentation" to achieve a task structure, e.g. a summary task and this will consist of sub-tasks
For this procedure it is necessary to use two icons on the Task tab namely Add Task Indentation/Remove Task Indentation (icons are formed by a green arrow).
See – an example

## Slide 17
MS Project WBS
Project management focus: Top-down and bottom-up planning
Top-down planning This approach identifies major phases or components of the project before filling in all the details required to complete those phases, which are represented in the plan as summary tasks. Complex plans can have several layers of nested summary tasks. This approach works from general to specific.
Bottom-up planning This approach identifies as many of the bottom-level detailed tasks as possible before outlining them into phases or summary tasks. This approach works from specific to general.
Creating accurate tasks and phases for most complex plans requires a combination of top-down and bottom-up planning. Typically, a project manager begins with established, broad phases for a plan (top-down planning), and the resources who
will execute the plan provide the detailed tasks that fill out each phase (bottom-up planning).

## Slide 18
MS Project WBS
In this way you create a sequential WBS (the corresponding column called "WBS code") of your entire project.

## Slide 19
MS Project WBS
For orientation in the project, the WBS is used, where summary tasks are created (e.g. points 1, 2, etc.), under them there are sub-tasks (activities), e.g. 2.1, 2.1.1.
This is a practical application of the WBS on a project example, where you have a specific problem (task) and you need more sub-activities to solve it, so break it down into individual "working packages".

## Slide 20
Vevox questions
https://silesianuniversity.vevox.com/#/meeting/449222/polls

## Slide 21
PART 3
MS Project tasks and durations
Demonstration of how to create tasks, define the duration of each task.
Tasks are the most basic building blocks of any project’s plan.
Tasks represent the work to be done to accomplish the goals of the project.
Tasks describe work in terms of dependencies, duration, and resource requirements.
In MS Project, there are several kinds of tasks. These include summary tasks, subtasks, and milestones.
What are called tasks in Project are sometimes more generally called activities or work packages.

## Slide 22
Create tasks
Tasks represent the work to be done to accomplish the goals of the project. Every task in a plan is given an ID number, but the number does not necessarily represent the order in which tasks occur.
Every task in Project has one of two scheduling modes that controls how the task is scheduled: manual (the default) or automatically scheduled.
Think of a manually scheduled task as an initial placeholder you can create at any time without affecting the rest of the schedule.
Task names should be recognizable and make sense to the people who will perform the tasks and to other stakeholders who will read the task names.
To enter task names
1. Click an empty cell in the Task Name column.
2. Enter your task names, and then press the Enter key after each one.
To insert a new task within a task list
1. Click in the Task Name column where you want to insert the new task.
2. On the Task tab, in the Insert group, click Task.
Project inserts a row for a new task and renumbers the subsequent tasks. Project
names the new task <New Task>.
3. With <New Task> selected, enter the task name, and then press Enter.
To delete a task
1. Right-click the task name, and then click Delete Task.

## Slide 23
Enter task durations and dates
A task’s duration represents the amount of time you expect it will take to complete the task. Project can work with task durations that range from minutes to months.
Project uses standard values for minutes and hours for durations: 1 minute equals 60 seconds, and 1 hour equals 60 minutes.
For the durations of days, weeks, and months, you can use Project’s defaults (for example, 20 days per month) or define your own values in the Project Options dialog box.

## Slide 24
Enter task durations and dates
Let’s explore task durations with an example. Assume that a plan has a project calendar with working time defined as 8:00 A.M. through 5:00 P.M., with one hour off for lunch breaks, Monday through Friday, leaving nonworking time defined as evenings (after 5:00 P.M.) and weekends.
If you estimate that a task will take 16 hours of working time, you could enter its duration as 2d to schedule work over two 8-hour workdays.
You should then expect that starting the task at 8:00 A.M. on a Friday means that it will not be completed until 5:00 P.M. on the following Monday. No work would be scheduled over the weekend because Saturday and Sunday have been defined as nonworking time.

## Slide 25
Enter task durations and dates
Project handles task scheduling in two ways.
Automatically scheduled tasks always have a duration (one day by default).
Manually scheduled tasks, however, do not initially have any duration. A task’s duration is essential for Project to schedule a task, so it makes sense that a manually scheduled task, which is not scheduled by Project, does not require a duration.
You can, however, enter placeholder duration values for manually scheduled tasks

## Slide 26
Enter task durations and dates
When you create an automatically scheduled task, Project adds a question mark (?) after the one-day duration to indicate that the duration is an estimate.
This is a handy reminder that you will need to determine the task’s correct duration at some point.
In fact, you can flag any task as having an estimated duration. Select the task, and on the Task tab, in the Properties group, click Information, and then select the Estimated check box.
If needed, you can schedule tasks to occur during nonworking and working time. To do this, enter an elapsed duration to a task. You enter elapsed duration by preceding the duration abbreviation with an e.
For instance, a construction project might have the tasks Pour foundation concrete and Remove foundation forms. If so, you might also want a task called Wait for concrete to cure, because you don’t want to remove the forms until the concrete has cured. The task Wait for concrete to cure should have an elapsed duration because the concrete will cure over a contiguous range of days, whether they are working or nonworking days. If the concrete takes 48 hours to cure, you can enter the duration for that task as 2ed, schedule the task to start on Friday at 9:00 A.M., and expect it to be complete by Sunday at 9:00 A.M

## Slide 27
Enter task durations and dates
To enter task duration
Click a cell in the Duration column for a task.
Enter a duration value.
Project initially sets all new tasks that have a duration value to start at the project start date. This is true whether the tasks are manually or automatically scheduled.
For manually scheduled tasks, you can enter a duration as either a numeric value, such as 2d, or as placeholder text, such as Check with Marketing team. For any columns that are too narrow to display the full value, point to the cell; its full value will appear in a ScreenTip.
For both manually and automatically scheduled tasks, Project draws a Gantt bar in the chart portion of a Gantt chart view. The length of the bar represents the task’s duration.

## Slide 28
Enter task durations and dates
Enter milestone tasks
In addition to entering tasks to be completed, you might want to account for an important event for your project’s plan, such as the end of a major phase of the project. To do this, you will create a milestone task.
Milestones are significant events that are either reached within the plan (such as the completion of a phase of work) or imposed upon the plan (such as a deadline by which to apply for funding). Because the milestone itself doesn’t normally include any work, milestones are normally represented as tasks with zero duration.

## Slide 29
Enter task durations and dates
Link tasks to create dependencies
When you link tasks, you create scheduling relationships between the tasks.
These task relationships are called dependencies, as in the start of this task is dependent upon the completion of a prior task. When you create task dependencies (also called links), Project can automatically adjust the scheduling of linked tasks as changes occur in your plan.
Creating dependencies by linking tasks is crucial to getting the full benefit of the Project scheduling engine.
These two tasks have a finish-to-start relationship, which has two aspects:
The second task must occur after the first task; this is a sequence.
The second task can occur only if the first task is completed; this is a dependency.

## Slide 30
Enter task durations and dates
Link tasks to create dependencies
Click View > Gantt Chart.
Hold down Ctrl and click the two tasks you want to link (in the Task Name column).
Click Task > Link the Selected Tasks Link Tasks button on the Task tab of the ribbon.

## Slide 31
Gantt chart with tasks and durations – an example

## Slide 32
Document task information
You can record additional information about a task in a note.
For example, you might have detailed descriptions of a task but want to keep the task’s name succinct.
You can add such details to a task note rather than to the task’s name. That way, the information resides in the plan and can be easily viewed or printed.
There are three types of notes: task notes, resource notes, and assignment notes.

## Slide 33
Vevox questions
https://silesianuniversity.vevox.com/#/meeting/449222/polls

## Slide 34
RECAP
The project manager is the key to successful project planning. It is desirable that the project manager be involved from project conception through execution.
Project planning must be systematic, flexible enough to handle unique activities, disciplined through reviews and controls, and capable of accepting multifunctional inputs. Successful project managers realize that project planning is an iterative process and must be performed throughout the life of the project.
One of the objectives of project planning is to completely define all work required (possibly through the development of a documented project plan) so that it will be readily identifiable to each project participant. This is a necessity in a project environment because:
  If the task is well understood prior to being performed, much of the work can be preplanned.
  If the task is not understood, then during the actual task execution more knowledge is gained that, in turn, leads to changes in resource allocations, schedules, and priorities.
  The more uncertain the task, the greater the amount of information that must be processed in order to ensure effective performance.